## Slide 1
Dr. SNS RAJALAKSHMI COLLEGE OF ARTS & SCIENCE (Autonomous)
Coimbatore -641049
Accredited by NAAC(Cycle–IV) with ‘A+’ Grade
(Recognized by UGC, Approved by AICTE, New Delhi and
Affiliated to Bharathiar University, Coimbatore)
DEPARTMENT OF MATHEMATICS
21UCL302: RESOURCE MANAGEMENT TECHNIQUES
II SEMESTER
TOPIC- PERT – Program Evaluation & Review technique
Ms. S.REKHA
ASSISTANT PROFESSOR
DEPARTMENT OF MATHS
Dr.SNSRCAS

## Slide 2
CPM and PERT are network based method design to assign in planning scheduling and control of projects.
A project is defined as a collection of activities which each activity consuming time and resources.
The objective of CPM and PERT is to provides analytical means for scheduling the activities.
The two techniques CPM and PERT which was developed indepently before in the CPM assumes probabilistic duration.
PERT – Program Evaluation & Review technique

## Slide 3
PERT AND ITS CALCULATION
The networks methods may be termed as deterministic since estimated activity time are assume to be expected variants. Deterministic network method assumes that the expected time is the actual time taken, on other end probabilistic method assume the reverse where the activity items are probability distribution of the activity time is based upon 3 different times estimate for each activates this as follows.
to – Optimistic time, is the shortest possible time to complete the activity if all those well.
tm – Most likely time, is a time estimate of normal time and activity would take.
tp - Pessimistic time, is a longer time that an activity would take (if everything goes wrong)
11/4/2025

## Slide 4
PERT AND ITS CALCULATION
The expected time (te) commonly refers to as the average (or) mean and its given by
te = to + 4 tm + tp / 6
the point m is free move between this two to and tp. The distribution of activity time is that for unmade distribution. The standard deviation can be estimated roughly as 1/6 of the range is given by
σ = tp – to / 6
and the variants of the activity time estimate is given by
σ = (tp-to/6)2
.
11/4/2025

## Slide 5
PERT AND ITS CALCULATION
11/4/2025
ALGORITHM FOR PERT
The various steps involves in PERT calculation are summarized as follows :
Step 1 : Identify each activity to complete as a result of the job requirement.
Step 2 : Construct an activity list in which the preceding and succeeding the sequence of activities is identified.
Step 3 : Draw a required network.
Step 4 : Denotes the time estimates to, tm, tp.
Step 5 : Using ∞, B, ∞ and B for the activity duration the expected time (te) for each activity is computed by using the formula.
te = to + 4tm + tp / 6

## Slide 6
PERT AND ITS CALCULATION
A Small project is complete of 7 activities whose time estimates are listed in the table as follows
Activity 1-2 1-3 1-4 2-5 3-5 4-6 5-6
to 1 1 2 1 2 2 3
tm 1 4 2 1 5 5 6
tp 7 7 8 1 14 8 15
1.Find the expected duration and variants for each activity
.
11/4/2025

## Slide 7
PERT AND ITS CALCULATION
11/4/2025
Activity | to | tm | tp | te = to+4tm+tp/6 | σ 2 = (tp-to/6)2
1-2 | 1 | 1 | 7 | 2 | 1
1-3 | 1 | 4 | 7 | 4 | 1
1-4 | 2 | 2 | 8 | 3 | 1
2-5 | 1 | 1 | 1 | 1 | 0
3-5 | 2 | 5 | 14 | 6 | 4
4-6 | 2 | 5 | 8 | 5 | 1
5-6 | 3 | 6 | 15 | 7 | 4

## Slide 8
PERT AND ITS CALCULATION
Variance =(tp-to/6)2
1. Variance =(tp-to/6)2
= (7- 1/6) ^2
=1
2. Variance =(tp-to/6)2
= (14- 2/6) ^2
=(12/6) ^2
= 4
11/4/2025

## Slide 9
PERT AND ITS CALCULATION
te = to + 4tm + tp / 6
te = to + 4tm + tp / 6
= (1+4*1+7)/6
=12/6
=2
2. te = to + 4tm + tp / 6
= (1+4*4+7)/6
=24/6
=4
11/4/2025

## Slide 10
PERT AND ITS CALCULATION
σ 2 =(tp-to/6)2
1. σ 2 =(tp-to/6)2
= (7- 1/6) ^2
=1
2. σ 2 =(tp-to/6)2
= (14- 2/6) ^2
=(12/6) ^2
= 4
11/4/2025

## Slide 11
PERT AND ITS CALCULATION
Variance =(tp-to/6)2
1. Variance =(tp-to/6)2
= (7- 1/6) ^2
=1
2. Variance =(tp-to/6)2
= (14- 2/6) ^2
=(12/6) ^2
= 4
11/4/2025

## Slide 12
Thank You