## SPM-H.C
Dr. SNS Rajalakshmi College of Arts and Science (Autonomous)
Coimbatore
Department: Computer Science
Class: II B.SC CS-A & B
Name of the Course: Software Project Management
Course Code: 21UCS804
Semester: IV
Regulation: 2022-2025
S. No. | Unit | Question | Mark | CO (I/II/III/IV/V) | Blooms Taxonomy Level
1 | I | Define the software project management and explain its importance | 4 | CO I | I
2 | I | Show the activities in softeware project management | 4 | CO I | I
3 | I | How to setting objectives in software project management? | 4 | CO I | I
4 | I | Classify the categorization of software projects | 4 | CO I | II
5 | I | Explain the software management principles | 4 | CO I | II
6 | I | Show the management controls in software project | 4 | CO I | II
7 | I | Construct the benefits of project portfolio management | 4 | CO I | III
8 | I | Identify the cost-benefit evaluation technology | 4 | CO I | III
9 | I | Apply the risk evaluation techniques in software project | 4 | CO I | III
10 | I | Examine the software strategic program management | 4 | CO I | IV
11 | I | Analyze the stepwise project planning in SPM | 4 | CO I | IV
12 | I | Simplify the advantages of project evaluation | 4 | CO I | IV
13 | II | What is software process and process model? | 4 | CO II | I
14 | II | Define SMART in software project management | 4 | CO II | I
15 | II | List out the types of process model and explain it any one | 4 | CO II | I
16 | II | Explain about mental delivery in SPM | 4 | CO II | II
17 | II | Give an outline about rapid application development | 4 | CO II | II
18 | II | Classify the stages of agile methods | 4 | CO II | II
19 | II | Apply the extreme programming in SPM | 4 | CO II | III
20 | II | Construct SCRUM methods in SPM | 4 | CO II | III
21 | II | Identify managing interactive processes in software process management | 4 | CO II | III
22 | II | Analyze the basics of software estimation in SPM | 4 | CO II | IV
23 | II | List out the effort and cost estimation techniques | 4 | CO II | IV
24 | II | Simplify the COSMIC full function points | 4 | CO II | IV
25 | III | List out the objectives of activity planning | 4 | CO III | I
26 | III | What is Project Schedules with example? | 4 | CO III | I
27 | III | Show the project activities in software project management | 4 | CO III | I
28 | III | Explain about sequencing and scheduling in software project | 4 | CO III | II
29 | III | Give an outline about network planning model | 4 | CO III | II
30 | III | Compare between forward pass & backward pass techniques | 4 | CO III | II
31 | III | Apply Critical Path (CRM) Method in software project | 4 | CO III | III
32 | III | Identify the Characteristics of PERT Technique | 4 | CO III | III
33 | III | Construct the monte carlo simulation in SPM | 4 | CO III | III
34 | III | Examine, how to allocate resources in software project? | 4 | CO III | IV
35 | III | Simplify the creation of critical patterns | 4 | CO III | IV
36 | III | Analyze the cost schedules in software project | 4 | CO III | IV
37 | IV | How to control the framework in software project management? | 4 | CO IV | I
38 | IV | What is collection of data project termination? | 4 | CO IV | I
39 | IV | Define Visualizing Progress with example | 4 | CO IV | I
40 | IV | Show the software project's cost monitoring | 4 | CO IV | II
41 | IV | Explain about earned value analysis in SPM | 4 | CO IV | II
42 | IV | Classify the tracking methods in software projects | 4 | CO IV | II
43 | IV | Solve the change control in project management | 4 | CO IV | III
44 | IV | Identify the software configuration management in project | 4 | CO IV | III
45 | IV | Develop the managing contracts in software project management | 4 | CO IV | III
46 | IV | Analyze the contract management in software project | 4 | CO IV | IV
47 | IV | Distinguish, 'How software projects different from other projects'? | 4 | CO IV | IV
48 | IV | List out the three activity of SPM and explain it | 4 | CO IV | IV
49 | V | What is the role of a project manager in staffing for a software project? | 4 | CO V | I
50 | V | How do you determine the required skill sets for the project team? | 4 | CO V | I
51 | V | List out the best methods of staff selection in SPM | 4 | CO V | I
52 | V | Show role does communication play in effective project staffing? | 4 | CO V | II
53 | V | Explain the importance of Feedback in the Oldham-Hackman Job Characteristic Model. | 4 | CO V | II
54 | V | Classify the different categories of decisions. | 4 | CO V | II
55 | V | Identify the methods used to improve motivation? | 4 | CO V | III
56 | V | Build to handle team members with varying levels of expertise and experience | 4 | CO V | III
57 | V | Select the organizational behaviour in software project | 4 | CO V | III
58 | V | Examine, 'How to work in a group'?and explain its advantage and disadvantage | 4 | CO V | IV
59 | V | Simplify the stages of team formation model. | 4 | CO V | IV
60 | V | List the various motivation theories. | 4 | CO V | IV
61 | I | Define the various activities covered by software project management. | 6 | CO I | I
62 | I | List the Outline of stepwise project planning. | 6 | CO I | I
63 | I | What are the activites involved by the management in detail? | 6 | CO I | I
64 | I | Give an outline of step wise planning activities for a project with neat diagram. | 6 | CO I | II
65 | I | Explain the difference between software projects and other projects in detail | 6 | CO I | II
66 | I | Classify the problems in software projects in detail | 6 | CO I | II
67 | I | Construct the management control in deatail | 6 | CO I | III
68 | I | Apply the setting objectives in detail | 6 | CO I | III
69 | I | Identify the objectives of project portfolio management | 6 | CO I | III
70 | I | Simplify the cost evaluation techniques and its methods with example | 6 | CO I | IV
71 | I | Analyze the risk evaluation with example | 6 | CO I | IV
72 | I | Examine the strategic program management and its process with example | 6 | CO I | IV
73 | II | Define the software process and explain its activities in detail | 6 | CO II | I
74 | II | List out the advantage and disadvantages of RAD model | 6 | CO II | I
75 | II | Show the agile model methodologies in detail | 6 | CO II | I
76 | II | Classify the phases of extreme programming | 6 | CO II | II
77 | II | Demonstrate the process flow of SCRUM | 6 | CO II | II
78 | II | Explain about the potential of iteractive process model | 6 | CO II | II
79 | II | Identify the basics of software estimation in detail | 6 | CO II | III
80 | II | Construct the effort and cost estimation techniques in details | 6 | CO II | III
81 | II | Apply the COSMIC full function points in software project | 6 | CO II | III
82 | II | Simplify the intermediate COCOMO model | 6 | CO II | IV
83 | II | Discover the short notes on V model with diagram | 6 | CO II | IV
84 | II | Examine the waterfall model in detail with diagram | 6 | CO II | IV
85 | III | What is objectives of activity planning and explain in detail? | 6 | CO III | I
86 | III | List out the importance of forward pass with an example | 6 | CO III | I
87 | III | How to evaluate the PERT techniques? | 6 | CO III | I
88 | III | Classify the approaches to identify the risk | 6 | CO III | II
89 | III | Illustrate, how critical path can be identified in precedence networks'? | 6 | CO III | II
90 | III | Explain in details about monte carlo simulation | 6 | CO III | II
91 | III | Construct the short notes on resource allocation and cost scheduling | 6 | CO III | III
92 | III | Identify the various responsibilities of a software project manager | 6 | CO III | III
93 | III | Select the advantages and disadvantages of software prototyping. | 6 | CO III | III
94 | III | Discover with an example how the effect of risk on project schedule is evaluated using PERT | 6 | CO III | IV
95 | III | Examine the impact of risk in a project. How is risk monitoring achieved to avoid failure in the project? | 6 | CO III | IV
96 | III | Simplify the use of brainstorming in identification of risks | 6 | CO III | IV
97 | IV | Define the framework for management and control in detail | 6 | CO IV | I
98 | IV | List out the various methods for visualizing the progress of a project | 6 | CO IV | I
99 | IV | Find out the importance of cost monitoring in detail | 6 | CO IV | I
100 | IV | Explain in detail about the method earned value analysis | 6 | CO IV | II
101 | IV | Summarize the project termination and explain why project termination is important? | 6 | CO IV | II
102 | IV | Interpret about change control and explain its four process. | 6 | CO IV | II
103 | IV | Construct the software configuration management and define its components | 6 | CO IV | III
104 | IV | Build the steps in managing the contracts in software projects | 6 | CO IV | III
105 | IV | Identify the stages in contract management and explain it detail | 6 | CO IV | III
106 | IV | Examine the types of contract with example | 6 | CO IV | IV
107 | IV | List out the advantage and disadvantages of contract management | 6 | CO IV | IV
108 | IV | Analyze the another way to categorize contract in detail | 6 | CO IV | IV
109 | V | List out the organizational behavior with example | 6 | CO V | I
110 | V | Define the recruitment process for choosing the right personfor a job | 6 | CO V | I
111 | V | Find the different models of motivation in detail | 6 | CO V | I
112 | V | Explain the expectancy theory of motivation with example | 6 | CO V | II
113 | V | Summarize the oldham-hackman job characteristic model states in detail | 6 | CO V | II
114 | V | Classify the various measurements of job design in project management | 6 | CO V | II
115 | V | Build the term decision making in the process of managing people and organizing teams | 6 | CO V | III
116 | V | Identify the measures to reduce the disadvantages of group decision making | 6 | CO V | III
117 | V | Construct the short notes on ethical and professional concerns | 6 | CO V | III
118 | V | Examine about the team structure and list out the advantage and disadvantage | 6 | CO V | IV
119 | V | Simplify the communication plan in software project with detail | 6 | CO V | IV
120 | V | Discover the virtual teams and explain why virtual team is important? | 6 | CO V | IV
121 | I | What is the difference between qualitative and quantitative data in project evaluation? | 10 | CO I | I
122 | I | Explain the step-wise project planning in detail with suitable flow chart | 10 | CO I | II
123 | I | Identify the three phases of project portfolio management and explain it detail | 10 | CO I | III
124 | I | Build the case study in challenges of project portfolio management | 10 | CO I | III
125 | I | Simplify the importance of project categorization, prioritization, and balancing within a portfolio | 10 | CO I | IV
126 | I | Inspect and analyze the common challenges faced in software project management. How can effective project management practices mitigate these challenges and contribute to project success? | 10 | CO I | IV
127 | II | List the role and principles of extreme programminge in detail | 10 | CO II | I
128 | II | Explain in detail about rapid application development with diagram | 10 | CO II | II
129 | II | Construct the agile model in detail with neat diagram | 10 | CO II | III
130 | II | Build the managing iteractive process model and list out the advantage and disadvantage | 10 | CO II | III
131 | II | Simplify the COSMIC concept and explain its 4 types | 10 | CO II | IV
132 | II | Examine the Spiral model in detail with diagram | 10 | CO II | IV
133 | III | How will you identify the major risks that might affect your project and identify the strategies for minimizing each of those risk? | 10 | CO III | I
134 | III | Explain in detail about the steps involved in project schedule | 10 | CO III | II
135 | III | Identify the role of activity planning in identifying and mitigating potential risks within a project | 10 | CO III | III
136 | III | Construct the Critical Path Method contribute to effective communication in CRM projects | 10 | CO III | III
137 | III | List out the different network planning models with example | 10 | CO III | IV
138 | III | Examine, 'How can project teams mitigate the impact of these factors to ensure a more accurate assessment of potential risks'? | 10 | CO III | IV
139 | IV | How does effective Software Configuration Management (SCM) contribute to project success? | 10 | CO IV | I
140 | IV | Explain,'How developers managed the resources during the termination phase? | 10 | CO IV | II
141 | IV | Identify,' How well-managed contracts contribute to project success, risk mitigation, and stakeholder satisfaction'? | 10 | CO IV | III
142 | IV | Construct,' How visual representations enhance communication, transparency, and decision-making throughout the project lifecycle'? | 10 | CO IV | III
143 | IV | Discover the case study for the challenge of visualizing progress in a complex software project | 10 | CO IV | IV
144 | IV | Simplify the common challenges faced in contract management for software projects | 10 | CO IV | IV
145 | V | How organizational behavior theories can guide the development of communication strategies that enhance information flow, understanding, and collaboration? | 10 | CO V | I
146 | V | Explain and evaluate various methods of staff selection in software project management. | 10 | CO V | II
147 | V | Identify,'How organizations can apply the Oldham-Hackman Job Characteristic Model in the design and restructuring of jobs'? | 10 | CO V | III
148 | V | Build the Role and Importance of Communication Plans in Software Project Management with example | 10 | CO V | III
149 | V | Analyzing the Dynamics, Challenges, and Strategies of Virtual Teams in Software Project Management | 10 | CO V | IV
150 | V | Examine the role of organizational behavior in the successful execution of software projects. | 10 | CO V | IV

## SPM-S.C
I | Define the software project management and explain its importance(CO:I)(BL:I) | 3
I | Show the activities in softeware project management(CO:I)(BL:I) | 3
I | How to setting objectives in software project management?(CO:I)(BL:I) | 3
I | Classify the categorization of software projects(CO:I)(BL:II) | 3
I | Explain the software management principles (CO:I)(BL:II) | 3
I | Show the management controls in software project (CO:I)(BL:II) | 3
I | Construct the benefits of project portfolio management(CO:I)(BL:III) | 3
I | Identify the cost-benefit evaluation technology (CO:I)(BL:III) | 3
I | Apply the risk evaluation techniques in software project(CO:I)(BL:III) | 3
I | Examine the software strategic program management (CO:I)(BL:IV) | 3
I | Analyze the stepwise project planning in SPM(CO:I)(BL:IV) | 3
I | Simplify the advantages of project evaluation(CO:I)(BL:IV) | 3
II | What is software process and process model?(CO:II)(BL:I) | 3
II | Define SMART in software project management(CO:II)(BL:I) | 3
II | List out the types of process model and explain it any one (CO:II)(BL:I) | 3
II | Explain about mental delivery in SPM(CO:II)(BL:II) | 3
II | Give an outline about rapid application development(CO:II)(BL:II) | 3
II | Classify the stages of agile methods (CO:II)(BL:II) | 3
II | Apply the extreme programming in SPM(CO:II)(BL:III) | 3
II | Construct SCRUM methods in SPM(CO:II)(BL:III) | 3
II | Identify managing interactive processes in software process management(CO:II)(BL:III) | 3
II | Analyze the basics of software estimation in SPM(CO:II)(BL:IV) | 3
II | List out the effort and cost estimation techniques(CO:II)(BL:IV) | 3
II | Simplify the COSMIC full function points (CO:II)(BL:IV) | 3
III | List out the objectives of activity planning(CO:III)(BL:I) | 3
III | What is Project Schedules with example?(CO:III)(BL:I) | 3
III | Show the project activities in software project management(CO:III)(BL:I) | 3
III | Explain about sequencing and scheduling in software project(CO:III)(BL:II) | 3
III | Give an outline about network planning model(CO:III)(BL:II) | 3
III | Compare between forward pass & backward pass techniques(CO:III)(BL:II) | 3
III | Apply Critical Path (CRM) Method in software project(CO:III)(BL:III) | 3
III | Identify the Characteristics of PERT Technique (CO:III)(BL:III) | 3
III | Construct the monte carlo simulation in SPM(CO:III)(BL:III) | 3
III | Examine, how to allocate resources in software project?(CO:III)(BL:IV) | 3
III | Simplify the creation of critical patterns(CO:III)(BL:IV) | 3
III | Analyze the cost schedules in software project(CO:III)(BL:IV) | 3
IV | How to control the framework in software project management?(CO:IV)(BL:I) | 3
IV | What is collection of data project termination?(CO:IV)(BL:I) | 3
IV | Define Visualizing Progress with example(CO:IV)(BL:I) | 3
IV | Show the software project's cost monitoring (CO:IV)(BL:II) | 3
IV | Explain about earned value analysis in SPM(CO:IV)(BL:II) | 3
IV | Classify the tracking methods in software projects(CO:IV)(BL:II) | 3
IV | Solve the change control in project management(CO:IV)(BL:III) | 3
IV | Identify the software configuration management in project(CO:IV)(BL:III) | 3
IV | Develop the managing contracts in software project management(CO:IV)(BL:III) | 3
IV | Analyze the contract management in software project(CO:IV)(BL:IV) | 3
IV | Distinguish, 'How software projects different from other projects'?(CO:IV)(BL:IV) | 3
IV | List out the three activity of SPM and explain it(CO:IV)(BL:IV) | 3
V | What is the role of a project manager in staffing for a software project?(CO:V)(BL:I) | 3
V | How do you determine the required skill sets for the project team?(CO:V)(BL:I) | 3
V | List out the best methods of staff selection in SPM(CO:V)(BL:I) | 3
V | Show role does communication play in effective project staffing?(CO:V)(BL:II) | 3
V | Explain the importance of Feedback in the Oldham-Hackman Job Characteristic Model(CO:V)(BL:II) | 3
V | Classify the different categories of decisions(CO:V)(BL:II) | 3
V | Identify the methods used to improve motivation?(CO:V)(BL:III) | 3
V | Build to handle team members with varying levels of expertise and experience(CO:V)(BL:III) | 3
V | Select the organizational behaviour in software project(CO:V)(BL:III) | 3
V | Examine, 'How to work in a group'? and explain its advantage and disadvantage (CO:V)(BL:IV) | 3
V | Simplify the stages of team formation model(CO:V)(BL:IV) | 3
V | List the various motivation theories.(CO:V)(BL:IV) | 3
I | Define the various activities covered by software project management(CO:I)(BL:I) | 6
I | List the Outline of stepwise project planning(CO:I)(BL:I) | 6
I | What are the activites involved by the management in detail?(CO:I)(BL:I) | 6
I | Give an outline of step wise planning activities for a project with neat diagram(CO:I)(BL:II) | 6
I | Explain the difference between software projects and other projects in detail(CO:I)(BL:II) | 6
I | Classify the problems in software projects in detail(CO:I)(BL:II) | 6
I | Construct the management control in deatail(CO:I)(BL:III) | 6
I | Apply the setting objectives in detail(CO:I)(BL:III) | 6
I | Identify the objectives of project portfolio management(CO:I)(BL:III) | 6
I | Simplify the cost evaluation techniques and its methods with example(CO:I)(BL:IV) | 6
I | Analyze the risk evaluation with example(CO:I)(BL:IV) | 6
I | Examine the strategic program management and its process with example(CO:I)(BL:IV) | 6
II | Define the software process and explain its activities in detail (CO:II)(BL:I) | 6
II | List out the advantage and disadvantages of RAD model(CO:II)(BL:I) | 6
II | Show the agile model methodologies in detail(CO:II)(BL:I) | 6
II | Classify the phases of extreme programming(CO:II)(BL:II) | 6
II | Demonstrate the process flow of SCRUM (CO:II)(BL:II) | 6
II | Explain about the potential of iteractive process model(CO:II)(BL:II) | 6
II | Identify the basics of software estimation in detail(CO:II)(BL:III) | 6
II | Construct the effort and cost estimation techniques in details(CO:II)(BL:III) | 6
II | Apply the COSMIC full function points in software project (CO:II)(BL:III) | 6
II | Simplify the intermediate COCOMO model(CO:II)(BL:IV) | 6
II | Discover the short notes on V model with diagram(CO:II)(BL:IV) | 6
II | Examine the waterfall model in detail with diagram(CO:II)(BL:IV) | 6
III | What is objectives of activity planning and explain in detail?(CO:III)(BL:I) | 6
III | List out the importance of forward pass with an example(CO:III)(BL:I) | 6
III | How to evaluate the PERT techniques? (CO:III)(BL:I) | 6
III | Classify the approaches to identify the risk(CO:III)(BL:II) | 6
III | Illustrate, how critical path can be identified in precedence networks'?(CO:III)(BL:II) | 6
III | Explain in details about monte carlo simulation(CO:III)(BL:III) | 6
III | Construct the short notes on resource allocation and cost scheduling(CO:III)(BL:III) | 6
III | Identify the various responsibilities of a software project manager(CO:III)(BL:III) | 6
III | Select the advantages and disadvantages of software prototyping(CO:III)(BL:IV) | 6
III | Discover with an example how the effect of risk on project schedule is evaluated using PERT (CO:III)(BL:IV) | 6
III | Examine the impact of risk in a project. How is risk monitoring achieved to avoid failure in the project?(CO:III)(BL:IV) | 6
III | Simplify the use of brainstorming in identification of risks(CO:III)(BL:IV) | 6
IV | Define the framework for management and control in detail(CO:IV)(BL:I) | 6
IV | List out the various methods for visualizing the progress of a project(CO:IV)(BL:I) | 6
IV | Find out the importance of cost monitoring in detail(CO:IV)(BL:I) | 6
IV | Explain in detail about the method earned value analysis(CO:IV)(BL:II) | 6
IV | Summarize the project termination and explain why project termination is important?(CO:IV)(BL:II) | 6
IV | Interpret about change control and explain its four process.(CO:IV)(BL:II) | 6
IV | Construct the software configuration management and define its components (CO:IV)(BL:III) | 6
IV | Build the steps in managing the contracts in software projects(CO:IV)(BL:III) | 6
IV | Identify the stages in contract management and explain it detail(CO:IV)(BL:III) | 6
IV | Examine the types of contract with example(CO:IV)(BL:IV) | 6
IV | List out the advantage and disadvantages of contract management(CO:IV)(BL:IV) | 6
IV | Analyze the another way to categorize contract in detail(CO:IV)(BL:IV) | 6
V | List out the organizational behavior with example (CO:V)(BL:I) | 6
V | Define the recruitment process for choosing the right person for a job(CO:V)(BL:I) | 6
V | Find the different models of motivation in detail(CO:V)(BL:I) | 6
V | Explain the expectancy theory of motivation with example(CO:V)(BL:II) | 6
V | Summarize the oldham-hackman job characteristic model states in detail(CO:V)(BL:II) | 6
V | Classify the various measurements of job design in project management(CO:V)(BL:II) | 6
V | Build the term decision making in the process of managing people and organizing teams(CO:V)(BL:III) | 6
V | Identify the measures to reduce the disadvantages of group decision making(CO:V)(BL:III) | 6
V | Construct the short notes on ethical and professional concerns(CO:V)(BL:III) | 6
V | Examine about the team structure and list out the advantage and disadvantage(CO:V)(BL:IV) | 6
V | Simplify the communication plan in software project with detail (CO:V)(BL:IV) | 6
V | Discover the virtual teams and explain why virtual team is important?(CO:V)(BL:IV) | 6
I | What is the difference between qualitative and quantitative data in project evaluation?(CO:I)(BL:I) | 10
I | Explain the step-wise project planning in detail with suitable flow chart(CO:I)(BL:II) | 10
I | Identify the three phases of project portfolio management and explain it detail(CO:I)(BL:III) | 10
I | Build the case study in challenges of project portfolio management(CO:I)(BL:III) | 10
I | Simplify the importance of project categorization, prioritization, and balancing within a portfolio (CO:I)(BL:IV) | 10
I | Inspect and analyze the common challenges faced in software project management. How can effective project management practices mitigate these challenges and contribute to project success?(CO:I)(BL:IV) | 10
II | List the role and principles of extreme programminge in detail(CO:II)(BL:I) | 10
II | Explain in detail about rapid application development with diagram(CO:II)(BL:II) | 10
II | Construct the agile model in detail with neat diagram(CO:II)(BL:III) | 10
II | Build the managing iteractive process model and list out the advantage and disadvantage(CO:II)(BL:III) | 10
II | Simplify the COSMIC concept and explain its 4 types (CO:II)(BL:IV) | 10
II | Examine the Spiral model in detail with diagram(CO:II)(BL:IV) | 10
III | How will you identify the major risks that might affect your project and identify the strategies for minimizing each of those risk?(CO:III)(BL:I) | 10
III | Explain in detail about the steps involved in project schedule(CO:III)(BL:II) | 10
III | Identify the role of activity planning in identifying and mitigating potential risks within a project (CO:III)(BL:III) | 10
III | Construct the Critical Path Method contribute to effective communication in CRM projects(CO:III)(BL:III) | 10
III | List out the different network planning models with example(CO:III)(BL:IV) | 10
III | Examine, 'How can project teams mitigate the impact of these factors to ensure a more accurate assessment of potential risks'?(CO:III)(BL:IV) | 10
IV | How does effective Software Configuration Management (SCM) contribute to project success?(CO:IV)(BL:I) | 10
IV | Explain,'How developers managed the resources during the termination phase?(CO:IV)(BL:II) | 10
IV | Identify,' How well-managed contracts contribute to project success, risk mitigation, and stakeholder satisfaction'?(CO:IV)(BL:III) | 10
IV | Construct,' How visual representations enhance communication, transparency, and decision-making throughout the project lifecycle'?(CO:IV)(BL:III) | 10
IV | Discover the case study for the challenge of visualizing progress in a complex software project (CO:IV)(BL:IV) | 10
IV | Simplify the common challenges faced in contract management for software projects (CO:IV)(BL:IV) | 10
V | How organizational behavior theories can guide the development of communication strategies that enhance information flow, understanding, and collaboration? (CO:V)(BL:I) | 10
V | Explain and evaluate various methods of staff selection in software project management(CO:V)(BL:II) | 10
V | Identify,'How organizations can apply the Oldham-Hackman Job Characteristic Model in the design and restructuring of jobs'?(CO:V)(BL:III) | 10
V | Build the Role and Importance of Communication Plans in Software Project Management with example(CO:V)(BL:III) | 10
V | Analyzing the Dynamics, Challenges, and Strategies of Virtual Teams in Software Project Management(CO:V)(BL:IV) | 10
V | Examine the role of organizational behavior in the successful execution of software projects(CO:V)(BL:IV) | 10